## Guide
Submission 2 - Test Case Design Sheet
Playwright QA Automation for Insurance Order Entry Platform
Purpose | Converts the Submission 1 QA plan into detailed, traceable test cases for the Playwright automation build.
Sheets | Test Cases (the design sheet) ¦ Coverage Summary ¦ Risk Traceability ¦ Validation ID Matrix ¦ Test Data ¦ Open Items ¦ Review Log (v2 reviewer findings)
Version | v2 - reviewed against all Submission 2 documents; 32 cases and 3 columns added, 8 cases rewritten. See Review Log.
Columns follow | Guideline section 5: ID/title, module and requirement/risk/defect link, preconditions, steps, expected result, severity/priority, evidence required, automation status.
Build Wave | 1 = smoke path and critical checks to automate first ¦ 2 = core validations ¦ 3 = extended coverage. The 'Short-Cohort Set' column (Y) marks the 30-35 test fallback.
Seeded defect links | The seeded defect catalog was not supplied. Column G holds the defect class described in the problem statement; replace with catalog codes once available.
Placeholders | 'CONFIRM' marks values (limits, formats, counts) that must be verified in the running app. See Open Items.
Automation Status | All cases start as 'Not started'. Update as specs are written (Automated / In progress / Blocked).
Extra columns | Scenario Type (Positive/Negative/Boundary), Backend Cross-check (API/DB), Isolation / Cleanup (independence and shared-state notes).
Editable cells | Yellow cells on Open Items, and the Automation Status / Execution Result / Notes columns on Test Cases.
Snapshot
Total test cases
Critical severity
P1 priority
Wave 1 (smoke)
Validation IDs covered
Open items

## Test Cases
Test Case ID | Title | Module | Test Type | Requirement / Validation ID | Risk ID (Sub 1) | Seeded Defect / Risk Link | Preconditions | Test Steps | Test Data | Expected Result | Severity | Priority | Build Wave | Tags | Evidence Required | Automation Status | Planned Spec File | Execution Result | Notes / Confirm | Short-Cohort Set | Scenario Type | Backend Cross-check (API/DB) | Isolation / Cleanup
TC-AUTH-01 | Valid agent logs in and lands on dashboard | Authentication | UI | AUTH-V01 | QR-01 | Valid agent cannot log in after auth change | App reachable; valid agent seeded; no active session. | 1. Open /login. 2. Enter valid username and password. 3. Click Sign in. | VALID_AGENT credentials from .env | Redirected to /dashboard; URL ends with /dashboard; agent greeting/name visible; no error message. | Critical | P1 | 1 | @smoke @regression auth | Screenshot of dashboard; trace on retry | Automated | tests/auth/login.spec.ts | Not run |  | Y | Positive | API: POST /api/auth/login returns 200 + token/session | Creates its own application via fixture (independent; unique generated data).
TC-AUTH-02 | Invalid password and unknown user show the same safe error and no session | Authentication | UI | AUTH-V02 | QR-01 | Misleading login error message | Valid agent exists; no session. | 1. Open /login. 2. Enter valid username with wrong password; submit. 3. Enter an unknown username with any password; submit. 4. Try opening /dashboard. | VALID_AGENT username + 'Wrong#Pass1'; 'no.such.user' + 'Wrong#Pass1' | Stays on /login; invalid-credentials message visible (not 'account locked'); /dashboard still redirects to /login. | High | P1 | 2 | @regression auth | Screenshot of error message | Automated | tests/auth/login.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-AUTH-03 | Blank username and password show mandatory-field errors | Authentication | UI | AUTH-V03 | QR-01 | Mandatory login validation missing | On /login with empty form. | 1. Leave username and password empty. 2. Click Sign in. | Empty values | Field-level required errors on both fields; no request treated as successful; stays on /login. | Medium | P2 | 2 | @regression auth | Screenshot of field errors | Automated | tests/auth/login.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-AUTH-04 | Logout clears session and protected routes redirect | Authentication | UI | AUTH-V04 | QR-01 | No logout session clearing | Logged in as valid agent. | 1. Click Logout. 2. Confirm redirect to /login. 3. Use browser Back. 4. Open /dashboard directly. | VALID_AGENT | Redirected to /login after logout; Back and direct /dashboard access redirect to /login; session cookie/token cleared. | Critical | P1 | 1 | @smoke @regression auth | Screenshot + cookie state note | Automated | tests/auth/session.spec.ts | Not run |  | Y | Positive | API: GET /api/applications returns 401 after logout | Creates its own application via fixture (independent; unique generated data).
TC-AUTH-05 | Direct access to protected routes without login is blocked | Authentication | UI | AUTH-V05 | QR-01 | Dashboard reachable without login | Fresh browser context, no cookies. | 1. Open /dashboard in a fresh context. 2. Open /applications/new. 3. Open /applications/<id>/review. | Seeded application id | Each URL redirects to /login; no dashboard or application data is rendered. | Critical | P1 | 1 | @smoke @regression auth | Screenshot; URL assertion in trace | Automated | tests/auth/session.spec.ts | Not run |  | Y | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-AUTH-06 | Locked user cannot access dashboard and sees accurate message | Authentication | UI | AUTH-V06 | QR-01 | Misleading locked message | Locked agent seeded. | 1. Open /login. 2. Enter locked agent credentials. 3. Click Sign in. 4. Open /dashboard. | LOCKED_AGENT credentials | Account-locked message shown (accurate wording); no session created; /dashboard redirects to /login. | High | P1 | 2 | @regression auth | Screenshot of locked message | Automated | tests/auth/lockout.spec.ts | Not run |  | N | Negative | - | Read-only: uses seeded locked agent.
TC-AUTH-07 | Account locks after five failed login attempts | Authentication | UI | AUTH-V07 | QR-01 | Lockout not enforced at 5 attempts | Dedicated non-locked test agent reserved for this test (lock state persists). | 1. Submit wrong password 4 times; confirm normal invalid message each time. 2. Submit wrong password a 5th time. 3. Submit the CORRECT password. | LOCKOUT_TEST_AGENT + wrong password | After the 5th failure the account is locked; correct password is then rejected with locked message. Lock is NOT triggered on attempt 4. | High | P1 | 2 | @regression auth | Screenshots after attempt 4, 5 and correct-password try | Automated | tests/auth/lockout.spec.ts | Not run |  | Y | Boundary | DB (if approved): failed_attempts / locked flag | Reserved LOCKOUT_TEST_AGENT; needs manual/admin unlock after run - run serially (workers=1 for this file).
TC-AUTH-08 | Weak password rejected during reset/change | Authentication | UI | AUTH-V08 | QR-01 | Weak password accepted | Reset/change password reachable (/forgot-password or profile). | 1. Start reset for a test agent. 2. Enter new password from weak set (short, no digit, no special, common word). 3. Submit. | 'abc', 'password', '12345678', 'Abcdefgh' | Each weak value rejected with a clear policy message; password not changed (old password still works). | High | P1 | 2 | @regression auth | Screenshot per weak value | Automated | tests/auth/password.spec.ts | Not run |  | N | Negative | - | Disposable agent; no password change persists on rejection.
TC-AUTH-09 | MFA agent completes login with simulated OTP | Authentication | UI | Guideline: reset OTP / MFA | QR-01 | MFA/OTP bypass or wrong-code acceptance | MFA agent seeded; OTP value known/simulated. | 1. Login as MFA agent. 2. Enter wrong OTP, observe error. 3. Enter correct OTP. | MFA_AGENT, OTP from .env (CONFIRM) | Wrong OTP rejected; correct OTP reaches /dashboard. | High | P2 | 3 | @regression auth | Screenshots of OTP error and dashboard | Automated | tests/auth/mfa.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-AUTH-10 | Password reset via OTP succeeds with valid new password | Authentication | UI | Guideline: reset OTP | QR-01 | Reset OTP flow broken | Disposable test agent; /forgot-password available. | 1. Open /forgot-password; enter username/email. 2. Enter simulated OTP. 3. Set compliant new password. 4. Login with new password. | Reset test agent; strong password | Reset completes; login with new password succeeds; old password no longer works. | Medium | P3 | 3 | @regression auth | Screenshots of each step | Automated | tests/auth/password.spec.ts | Not run |  | N | Positive | - | Disposable reset agent; password restored in afterEach.
TC-AUTH-11 | Reusing the same password on reset is rejected | Authentication | UI | Guideline: same password reuse | QR-01 | Same-password reuse allowed | Disposable test agent with known current password. | 1. Start password reset/change. 2. Enter new password identical to current password. 3. Submit. | Current password | Request rejected with a 'cannot reuse' message; password unchanged. | Medium | P3 | 3 | @regression auth | Screenshot of rejection | Automated | tests/auth/password.spec.ts | Not run |  | N | Negative | - | Disposable reset agent; password restored in afterEach.
TC-AUTH-12 | Expired/timed-out session forces re-login without data exposure | Authentication | UI | Spec: session timeout / Sub 1 path 'Session expiration' | QR-01, QR-10 | Session not invalidated on timeout | Logged in; session lifetime known (CONFIRM) or session cookie can be cleared/expired in the test. | 1. Login and open an application step with unsaved edits. 2. Expire the session (wait for timeout or delete/expire the session cookie via context). 3. Click Save or navigate to another step. 4. Re-login. | VALID_AGENT | User is redirected to /login; no protected data rendered; API calls return 401; after re-login the previously SAVED data is intact and unsaved edits are not silently stored. | High | P2 | 3 | @regression auth | Screenshot of redirect; network log showing 401 | Automated | tests/auth/session.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-AUTH-13 | Pending (unapproved) agent cannot access the platform | Authentication | UI | Spec: user type 'pending agent' | QR-01 | Unapproved account gains access | Pending agent seeded. | 1. Login with pending agent credentials. 2. Open /dashboard. | PENDING_AGENT | Access is denied with an accurate pending-approval message (behavior CONFIRM); no session granted; /dashboard redirects to /login. | High | P2 | 3 | @regression auth | Screenshot of message | Automated | tests/auth/login.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-DASH-01 | Dashboard shows summaries and New Application CTA after login | Dashboard | UI | DASH-V01 | QR-02 | Dashboard summary missing/incorrect | Logged in as valid agent with seeded applications. | 1. Login as valid agent. 2. Observe dashboard. | VALID_AGENT | Draft summary, submitted summary and 'New application' CTA are visible. | High | P1 | 1 | @smoke @regression dashboard | Screenshot of dashboard | Automated | tests/dashboard/dashboard.spec.ts | Not run |  | Y | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-DASH-02 | Agent sees only own applications (UI isolation) | Dashboard | UI | DASH-V02 | QR-02 | Agent sees other agents' applications | Two valid agents each with distinct seeded applications. | 1. Login as agent A; record application IDs. 2. Logout; login as agent B; record IDs. 3. Compare lists. | VALID_AGENT, SECOND_AGENT | The two ID sets do not overlap; neither agent sees the other's applications. | Critical | P1 | 2 | @regression dashboard | Screenshots of both lists | Automated | tests/dashboard/dashboard.spec.ts | Not run |  | Y | Negative | - | Read-only seeded applications of two agents.
TC-DASH-03 | New agent sees empty-state message and CTA | Dashboard | UI | DASH-V03 | QR-02 | Empty state not handled | New agent with zero applications. | 1. Login as new agent. | NEW_AGENT | Empty-state copy shown; CTA to start a new application visible; no rows rendered. | Low | P3 | 3 | @regression dashboard | Screenshot of empty state | Automated | tests/dashboard/dashboard.spec.ts | Not run |  | N | Positive | - | Read-only: new agent has no applications.
TC-DASH-04 | Draft can be resumed with previously entered data | Dashboard | UI | DASH-V04 | QR-02, QR-10 | Draft not resumable / not persisted | Seeded draft application owned by valid agent (or created in test). | 1. From dashboard open the draft row. 2. Inspect the step and field values. | Seeded draft id | Application opens at the saved step; previously saved values are present and unchanged. | High | P1 | 2 | @regression dashboard | Screenshot of restored values | Automated | tests/dashboard/dashboard.spec.ts | Not run |  | N | Positive | API/DB: saved draft values | Read-only seeded draft (or draft created by fixture).
TC-DASH-05 | Status filter returns correct rows (Draft/Submitted/Approved) | Dashboard | UI | DASH-V05 | QR-02 | Filters return wrong rows | Seeded draft, submitted and approved applications. | 1. Apply Draft filter; read rows. 2. Apply Submitted filter. 3. Apply Approved filter. | Seeded applications of each status | Each filter shows only rows of that status; counts match seed data. | Medium | P2 | 2 | @regression dashboard | Screenshot per filter | Automated | tests/dashboard/dashboard.spec.ts | Not run |  | N | Positive | - | Read-only seeded applications of each status.
TC-DASH-06 | Dashboard status matches status API for each application (status endpoint) | Dashboard | UI | DASH-V06 | QR-02, QR-09 | Dashboard status differs from backend | Valid agent logged in; session available to request context. | 1. Read each dashboard row id + status. 2. Call GET /api/applications/{id}/status for each. 3. Compare. | Seeded applications | Every UI status equals API status. | High | P1 | 2 | @regression dashboard @api | Table of UI vs API values in test log | Automated | tests/dashboard/dashboard-api.spec.ts | Not run |  | N | Positive | API: GET /api/applications/{id}/status | Creates its own application via fixture (independent; unique generated data).
TC-DASH-07 | Dashboard search finds an application by name/reference | Dashboard | UI | Spec: dashboard search | QR-02 | Search returns wrong rows | Seeded applications with distinct client names/references. | 1. Search by a known client name. 2. Search by a known reference/ID. 3. Search for a non-existent term. 4. Clear search. | Seeded names/references | Matching rows only for 1 and 2; empty-result message for 3; full list restored after 4. | Medium | P2 | 3 | @regression dashboard | Screenshots of each result state | Automated | tests/dashboard/dashboard.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-DASH-08 | Agent cannot open another agent's application by direct URL | Dashboard | UI | Risk QR-02 (isolation) | QR-02, QR-01 | Agent sees other agents' applications | Application id owned by agent A; agent B logged in. | 1. As agent B open /applications/<A's id>. 2. Open /applications/<A's id>/review and /status. | SECOND_AGENT + VALID_AGENT application id | Access denied (403/404 page or redirect); no data of agent A is rendered on any of the three routes. | Critical | P1 | 2 | @regression dashboard auth | Screenshots + network status codes | Automated | tests/dashboard/isolation.spec.ts | Not run |  | Y | Negative | API: GET /api/applications/{otherId} returns 403/404 | Creates its own application via fixture (independent; unique generated data).
TC-DASH-09 | Profile and Support pages load for a logged-in agent and are protected when logged out | Dashboard | UI | Routes /profile, /support | QR-01 | Support/profile route unprotected or broken | Valid agent; fresh context for the logged-out part. | 1. Login; open /profile and /support. 2. In a fresh context open both URLs. | VALID_AGENT | Both pages render for the logged-in agent; logged-out access redirects to /login. | Low | P3 | 3 | @regression dashboard auth | Screenshots | Automated | tests/dashboard/dashboard.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-CLI-01 | Valid insured personal information is saved and Next is enabled | Client Information | UI | CLI-V01 | QR-03, QR-10 | Valid data blocks progression | Logged in; new application started. | 1. Fill all mandatory client fields with valid data. 2. Click Save/Next. 3. Return to the step. | Generated client (age 40) | Next step becomes enabled; saved values persist when step is revisited. | High | P1 | 1 | @smoke @regression client | Screenshot of filled form + revisit | Automated | tests/client-information/client.spec.ts | Not run |  | Y | Positive | API: GET client returns saved values | Creates its own application via fixture (independent; unique generated data).
TC-CLI-02 | Mandatory personal fields show inline errors | Client Information | UI | CLI-V02 | QR-03 | Mandatory fields skipped | On Client step with empty form. | 1. Leave name, DOB, gender, marital status, nationality, occupation, employer blank. 2. Click Next. | Empty form | Each required field shows an inline error; progression blocked. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression client | Screenshot of errors | Automated | tests/client-information/client.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-CLI-03 | DOB making client under 18 is rejected | Client Information | UI | CLI-V03 | QR-03 | Age eligibility rule missed | On Client step. | 1. Enter DOB = today minus 18 years plus 1 day (17y 364d). 2. Attempt to proceed. | DOB 17y364d | Eligibility error displayed; progression blocked. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Critical | P1 | 2 | @regression client | Screenshot of error | Automated | tests/client-information/dob.spec.ts | Not run |  | Y | Boundary | API: POST client rejects the same DOB (see TC-API-15) | Creates its own application via fixture (independent; unique generated data).
TC-CLI-04 | DOB making client over 65 is rejected | Client Information | UI | CLI-V04 | QR-03 | Age eligibility rule missed | On Client step. | 1. Enter DOB = 65 years and 1 day ago. 2. Attempt to proceed. | DOB 65y+1d (CONFIRM inclusivity of 65) | Eligibility error displayed; progression blocked. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Critical | P1 | 2 | @regression client | Screenshot of error | Automated | tests/client-information/dob.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | Y | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-CLI-05 | Future DOB is rejected | Client Information | UI | CLI-V05 | QR-03 | Future DOB accepted | On Client step. | 1. Enter DOB = tomorrow. 2. Attempt to proceed. | DOB tomorrow | Validation error shown; progression blocked. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Critical | P1 | 1 | @smoke @regression client | Screenshot of error | Automated | tests/client-information/dob.spec.ts | Not run |  | Y | Boundary | API: POST client rejects future DOB | Creates its own application via fixture (independent; unique generated data).
TC-CLI-06 | Boundary ages 18 and 65 are accepted (inclusive boundary) | Client Information | UI | Guideline: DOB rules (BVA) | QR-03 | Boundary off-by-one | On Client step. Inclusivity of 18 and 65 confirmed (see Open Items). | 1. Enter DOB exactly 18 years ago; proceed. 2. Repeat with DOB exactly 65 years ago. | DOB 18y0d and 65y0d | Both DOBs accepted and progression allowed (adjust if spec says 65 exclusive). Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 3 | @regression client | Screenshots for both boundaries | Automated | tests/client-information/dob.spec.ts | Not run |  | N | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-CLI-07 | Calculated age is displayed correctly from DOB | Client Information | UI | Guideline: age visibility | QR-03 | Age miscalculated | On Client step. | 1. Enter a DOB giving a known age (including one whose birthday is later this year). 2. Read displayed age. | DOB 40y and 39y364d | Displayed age equals expected age computed by test helper for each DOB. | High | P2 | 2 | @regression client | Screenshot of age field | Automated | tests/client-information/dob.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-CLI-08 | Invalid name formats are rejected | Client Information | UI | Guideline: name validation | QR-03 | Invalid names accepted | On Client step. | 1. Enter names with digits/symbols (e.g. 'J0hn#', '123', single space). 2. Attempt to proceed. | 'J0hn#', '12345', ' ' | Name validation error shown for each invalid value; valid name 'Anita Rao' accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 3 | @regression client | Screenshot per invalid value | Automated | tests/client-information/client.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-CLI-09 | Impossible or malformed DOB values are rejected | Client Information | UI | Guideline: date of birth rules | QR-03 | Invalid DOB accepted | On Client step. | 1. Enter 31-Feb, 00/00/0000, text 'abc', and a year before 1900. 2. Attempt to proceed. | '31-02-1990', '00-00-0000', 'abc', '01-01-1850' | Each value is rejected with a date-format/range error; no age is calculated or displayed. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 3 | @regression client | Screenshot per value | Automated | tests/client-information/dob.spec.ts | Not run |  | N | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-ADDR-01 | Same-as-residential copies address to mailing | Address & Contact | UI | CLI-V06 | QR-03 | Same-as-residential not copied | On Address & Contact step. | 1. Fill residential address. 2. Tick 'same as residential'. 3. Compare mailing fields. 4. Save and reopen. | Generated address | All mailing fields equal residential values; values persist after reopening. | Medium | P1 | 1 | @smoke @regression address | Screenshot of copied fields | Automated | tests/client-information/address.spec.ts | Not run |  | Y | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-ADDR-02 | Unticking same-as-residential makes mailing editable and independent | Address & Contact | UI | Guideline: same-as-residential | QR-03 | Mailing locked/overwritten | Same-as-residential ticked. | 1. Untick the checkbox. 2. Edit a mailing field. 3. Edit a residential field. | Generated address | Mailing fields become editable; editing residential no longer overwrites edited mailing values. | Low | P3 | 3 | @regression address | Screenshot | Automated | tests/client-information/address.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-ADDR-03 | Invalid ZIP/postal code is rejected | Address & Contact | UI | Guideline: ZIP validation | QR-03 | ZIP validation gaps | On Address step. | 1. Enter invalid ZIP values. 2. Attempt to proceed. | 'ABCDE', '123', '1234567', blank | Error shown per invalid ZIP; valid ZIP for the chosen state accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 2 | @regression address | Screenshot per value | Automated | tests/client-information/address.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-ADDR-04 | State is mandatory and ZIP/state mismatch is flagged | Address & Contact | UI | Guideline: state validation | QR-03 | State validation gaps | On Address step. | 1. Leave state unselected; proceed. 2. Select a state and a ZIP belonging to another state (if app validates). | State/ZIP pairs (CONFIRM rule) | Missing state blocks progression; mismatch behavior matches confirmed rule. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P3 | 3 | @regression address | Screenshot | Automated | tests/client-information/address.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-ADDR-05 | Invalid email format is rejected | Address & Contact | UI | CLI-V07 | QR-03 | Email validation gap | On Contact section. | 1. Enter invalid emails. 2. Attempt to proceed. | 'abc', 'a@b', 'a@@b.com', 'a b@c.com' | Inline email error per value; valid email accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 2 | @regression address | Screenshot per value | Automated | tests/client-information/contact.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-ADDR-06 | Invalid phone number is rejected | Address & Contact | UI | CLI-V07 | QR-03 | Phone validation gap | On Contact section. | 1. Enter invalid mobile/alternate numbers. 2. Attempt to proceed. | '12345', 'abcdefghij', '+', 11-digit value (CONFIRM format) | Inline phone error per value; valid number accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 2 | @regression address | Screenshot per value | Automated | tests/client-information/contact.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-ADDR-07 | At least one contact method / preferred mode is required | Address & Contact | UI | Guideline: mandatory contact method | QR-03 | No contact method required | On Contact section. | 1. Clear email, mobile and alternate phone. 2. Leave preferred communication mode empty. 3. Proceed. | Empty contact data | Validation requires a contact method / preferred mode; progression blocked. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 3 | @regression address | Screenshot | Automated | tests/client-information/contact.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-KYC-01 | SSN is masked after entry (only last four visible) | KYC & Financial | UI | CLI-V08 | QR-04 | SSN not masked | On KYC step. | 1. Enter a synthetic SSN. 2. Tab away / save. 3. Reopen the step. | Synthetic SSN 123-45-6789 (fake) | Only last four digits visible after entry and on reopen; full value not displayed. | Critical | P1 | 2 | @regression kyc | Screenshot (use fake SSN only) | Automated | tests/client-information/kyc.spec.ts | Not run |  | Y | Positive | API/DB: stored SSN masked/encrypted (read-only) | Creates its own application via fixture (independent; unique generated data).
TC-KYC-02 | ID number validated by ID type | KYC & Financial | UI | Risk QR-04 | QR-04 | ID format not validated by type | On KYC step; ID types available (CONFIRM list). | 1. For each ID type enter a number in the wrong format. 2. Attempt to proceed. 3. Enter correct format. | Wrong/right format per ID type | Wrong formats rejected with type-specific error; correct formats accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 3 | @regression kyc | Screenshot per ID type | Automated | tests/client-information/kyc.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-KYC-03 | KYC upload rejects unsupported file type | KYC & Financial | UI | CLI-V09 | QR-04, QR-08 | Bad file types accepted | On KYC document upload control. | 1. Upload sample.exe. 2. Upload sample.txt. | invalid-type files from fixtures/files | Both uploads rejected with unsupported-type message; no document listed as uploaded. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression kyc | Screenshot of error | Automated | tests/client-information/kyc.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-KYC-04 | PEP 'Yes' makes details mandatory | KYC & Financial | UI | CLI-V10 | QR-04 | PEP details optional | On Compliance section. | 1. Select PEP = Yes. 2. Leave details blank and proceed. 3. Fill details and proceed. | PEP detail text | Details field appears and is mandatory; blank blocks progression; filled allows. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression kyc | Screenshots before/after | Automated | tests/client-information/kyc.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-KYC-05 | Income vs premium affordability validation is applied | KYC & Financial | UI | Risk QR-04 / QR-05 | QR-04, QR-05 | Affordability not applied | Client with low annual income; product configured with high premium. | 1. Enter low income on KYC step. 2. Configure product so annual premium exceeds affordability threshold (CONFIRM). 3. Proceed to review. | Income 100000 (example), high face value | Affordability warning or block displayed according to confirmed rule. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 3 | @regression kyc | Screenshot of warning | Automated | tests/client-information/kyc.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-KYC-06 | Incomplete compliance declaration blocks progression | KYC & Financial | UI | Functional spec: Compliance | QR-04 | Declaration not enforced | On KYC step. | 1. Leave PEP/declaration unanswered. 2. Proceed. | Empty declaration | Progression blocked with message on unanswered declaration. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 3 | @regression kyc | Screenshot | Automated | tests/client-information/kyc.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-KYC-07 | Sensitive ID is not returned unmasked in client API response | KYC & Financial | API | Spec: SSN masking | QR-04 | SSN exposed in response | Application with saved SSN; authenticated request context. | 1. GET /api/applications/{id}/client. 2. Inspect SSN field(s). | Application from TC-KYC-01 | SSN returned masked (last four only) or absent; full value not present anywhere in body. | Critical | P1 | 2 | @api @regression kyc | Response body saved with value redacted | Automated | tests/api/client-api.spec.ts | Not run |  | Y | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-KYC-08 | Financial suitability fields are mandatory and numeric-validated | KYC & Financial | UI | Spec: income, net worth, source of funds, risk profile | QR-04 | Financial fields skipped / invalid values accepted | On KYC step. | 1. Leave income, net worth, source of funds and risk profile empty; proceed. 2. Enter negative and non-numeric income/net worth; proceed. 3. Enter valid values. | Empty; -1; 'abc'; valid income and net worth | Empty and invalid values blocked with field-level errors; valid values accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 2 | @regression kyc | Screenshots | Automated | tests/client-information/kyc.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-KYC-09 | ID issue/expiry dates are validated | KYC & Financial | UI | Spec: ID issue/expiry date | QR-04 | Expired or inconsistent ID accepted | On KYC step. | 1. Enter an expiry date in the past. 2. Enter expiry earlier than issue date. 3. Enter issue date in the future. 4. Enter valid dates. | Past expiry; expiry < issue; future issue; valid | Cases 1-3 rejected with clear errors (rule CONFIRM); valid dates accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 3 | @regression kyc | Screenshots | Automated | tests/client-information/kyc.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-01 | Catalog lists expected Whole Life products | Product & Policy | UI | PROD-V01 | QR-05 | Product missing/wrong in catalog | Logged in; /products reachable. | 1. Open /products. 2. Read product cards. | Expected product names (from seed, CONFIRM) | Expected active products are shown with names and key details. | Medium | P2 | 2 | @regression product | Screenshot of catalog | Automated | tests/product-selection/catalog.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-02 | Product detail page shows features, eligibility and limits | Product & Policy | UI | PROD-V02 | QR-05 | Product detail incorrect | On /products. | 1. Click a product. 2. Read detail page. | First active product | /products/:id opens; features, eligibility and coverage limits visible. | Medium | P3 | 2 | @regression product | Screenshot of detail page | Automated | tests/product-selection/catalog.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-03 | Face value below minimum is rejected | Product & Policy | UI | PROD-V03 | QR-05 | Face value minimum not enforced | Product selected; limits known (CONFIRM). | 1. Enter face value = min - 1. 2. Attempt to save. 3. Enter exactly min. | MIN_FACE_VALUE (from product detail) | min-1 rejected with validation; exactly min accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression product | Screenshots of both boundaries | Automated | tests/product-selection/face-value.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-04 | Face value above maximum is rejected | Product & Policy | UI | PROD-V04 | QR-05 | Face value maximum not enforced | Product selected; limits known. | 1. Enter face value = max + 1. 2. Attempt to save. 3. Enter exactly max. | MAX_FACE_VALUE | max+1 rejected with validation; exactly max accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression product | Screenshots of both boundaries | Automated | tests/product-selection/face-value.spec.ts | Not run |  | N | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-05 | Premium recalculates when frequency changes | Product & Policy | UI | PROD-V05 | QR-05 | Premium not recalculated on frequency change | Valid face value entered. | 1. Note premium for Monthly. 2. Switch to Quarterly, Semi-annual, Annual and note each. | Fixed face value | Displayed premium changes for each frequency and matches API/formula once confirmed. | High | P1 | 2 | @regression product | Table of frequency vs premium in log | Automated | tests/product-selection/premium.spec.ts | Not run |  | Y | Positive | API: premium field (if exposed) | Creates its own application via fixture (independent; unique generated data).
TC-PROD-06 | Review-page premium equals configuration-page premium | Product & Policy | UI | PROD-V06 | QR-05 | Review premium differs from config | Application configured through product step. | 1. Capture premium on configuration page. 2. Navigate to /review. 3. Compare. | Configured application | Premium values are identical (same currency/rounding). | High | P1 | 2 | @regression product | Screenshots of both pages | Automated | tests/product-selection/premium.spec.ts | Not run |  | Y | Positive | API: premium on review payload | Creates its own application via fixture (independent; unique generated data).
TC-PROD-07 | Suitability warning appears for risk-profile mismatch | Product & Policy | UI | PROD-V07 | QR-05 | No suitability warning | KYC risk profile set to conservative; high-risk product/amount chosen. | 1. Set risk profile on KYC. 2. Select mismatching product/face value. | Risk profile = low (CONFIRM) | Suitability warning visible. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 3 | @regression product | Screenshot of warning | Automated | tests/product-selection/suitability.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-08 | Inactive product cannot be selected | Product & Policy | UI | Guideline: inactive products | QR-05 | Inactive product selectable | At least one inactive product in seed data (CONFIRM). | 1. Look for inactive product in catalog. 2. Try to select/configure it (UI and direct URL). | Inactive product id | Inactive product is hidden or select action disabled; direct URL/API does not allow configuration. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 3 | @regression product | Screenshot | Automated | tests/product-selection/catalog.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-09 | Saved product configuration persists after reopening | Product & Policy | UI | Guideline: persistence checks | QR-10 | Configuration not persisted | Application with product configured and saved. | 1. Save product configuration. 2. Go to dashboard and resume. 3. Open product step. | Face value, frequency, payment term, policy term | All configured values and premium are restored exactly. | High | P2 | 3 | @regression product | Screenshot of restored values | Automated | tests/product-selection/persistence.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-10 | Product eligibility is validated against client age | Product & Policy | UI | Problem statement 2.2: product eligibility vs age | QR-05 | Product eligibility not validated against client age | Product with an age eligibility range visible on detail page (CONFIRM). | 1. Create application with client age outside the product's range. 2. Try to select that product. 3. Repeat with an in-range age. | Out-of-range and in-range ages | Out-of-range selection blocked or warned; in-range accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression product | Screenshots | Automated | tests/product-selection/eligibility.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-11 | Payment term and policy term options follow product rules | Product & Policy | UI | Spec: payment term / policy term | QR-05 | Term rules not enforced | Product selected. | 1. Open payment term dropdown; read options. 2. Select each option and check the dependent policy-term display (Whole Life / to Age 100). 3. Attempt an unsupported combination if the UI allows. | All payment term options | Dropdown values match product detail/API; policy term display follows the rule; unsupported combos blocked. | Medium | P2 | 3 | @regression product | Screenshot of options | Automated | tests/product-selection/terms.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-12 | Invalid face value inputs (zero, negative, non-numeric, decimals) are rejected | Product & Policy | UI | Spec: face value boundary validation | QR-05 | Face value validation gaps | Product selected. | 1. Enter 0, -1000, 'abc', 100000.55 (if integers only), and blank. 2. Attempt to save. | 0; -1000; 'abc'; 100000.55; blank | Each value rejected with a face-value error; premium not calculated from invalid input. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Medium | P2 | 3 | @regression product | Screenshot per value | Automated | tests/product-selection/face-value.spec.ts | Not run |  | N | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-13 | Product search/filter in catalog returns correct products | Product & Policy | UI | ProductCatalogPage: product search | QR-05 | Search returns wrong products | On /products. | 1. Search for an existing product name. 2. Search for a non-existent term. 3. Clear the search. | Existing / non-existent term | Only matching products for 1; empty-result message for 2; full catalog after 3. | Low | P3 | 3 | @regression product | Screenshots | Automated | tests/product-selection/catalog.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-PROD-14 | Premium shown in UI equals premium from API (reconciliation) | Product & Policy | UI | Spec: premium UI/API reconciliation | QR-05, QR-09 | UI and API premium differ | Configured application; premium exposed by API (CONFIRM field). | 1. Configure face value + frequency. 2. Read UI premium. 3. GET application/product data from API and read premium. 4. Compare for all four frequencies. | Fixed configuration x 4 frequencies | UI premium equals API premium for each frequency (same rounding). | High | P2 | 3 | @regression product @api | UI vs API comparison table | Automated | tests/product-selection/premium.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-RID-01 | Eligible protection rider (ADB) can be added | Riders | UI | RIDER-V01 | QR-06 | Rider add fails | Application at Riders step; client age eligible. | 1. Select the ADB rider. 2. Check premium summary. | Eligible client age 40 | Rider appears in premium summary. | High | P1 | 1 | @smoke @regression rider | Screenshot of premium summary | Automated | tests/riders/riders.spec.ts | Not run |  | Y | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-RID-02 | Rider coverage cannot exceed base face value | Riders | UI | RIDER-V02 | QR-06 | Rider coverage above face value | Face value set (e.g. 100000). | 1. Select rider with editable coverage. 2. Enter coverage = face value + 1. 3. Enter coverage = face value. | Coverage FV+1 and FV | FV+1 rejected with validation; FV accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression rider | Screenshots | Automated | tests/riders/riders.spec.ts | Not run |  | Y | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-RID-03 | Age-ineligible rider cannot be added | Riders | UI | RIDER-V03 | QR-06 | Age-ineligible rider added | Client age outside rider's allowed range (CONFIRM limits). | 1. Reach Riders step with out-of-range age client. 2. Try to select rider. | Client near upper age limit | Rider disabled or error shown; not added to summary. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 3 | @regression rider | Screenshot | Automated | tests/riders/riders.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-RID-04 | Maximum rider count is enforced | Riders | UI | RIDER-V04 | QR-06 | Max rider count ignored | Max count known (CONFIRM). | 1. Add riders until max. 2. Try to add one more. | Riders list | Blocking message shown; extra rider not added. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 3 | @regression rider | Screenshot of block message | Automated | tests/riders/riders.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-RID-05 | Mutually exclusive waiver riders cannot both be selected | Riders | UI | RIDER-V05 | QR-06 | Exclusive waivers both allowed | Two waiver riders exist. | 1. Select waiver rider A. 2. Try to select waiver rider B. | Waiver riders | Waiver B disabled or blocked while A selected. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression rider | Screenshot | Automated | tests/riders/riders.spec.ts | Not run |  | Y | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-RID-06 | Critical illness rider triggers health questionnaire | Riders | UI | RIDER-V06 | QR-06 | CI questionnaire missing | CI rider available to client. | 1. Select Critical Illness rider. | CI rider | Health questionnaire section appears and is required. | Medium | P2 | 2 | @regression rider | Screenshot of questionnaire | Automated | tests/riders/riders.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-RID-07 | Rider premium is itemized and total updates | Riders | UI | RIDER-V07 | QR-06, QR-05 | Premium not itemized | Base premium known. | 1. Note base premium. 2. Add a rider. 3. Read itemized lines and total. | ADB rider | Rider line item displayed; total = base + rider premium. | High | P1 | 2 | @regression rider | Screenshot of itemization | Automated | tests/riders/riders.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-RID-08 | Rider dependency rules are enforced | Riders | UI | Spec: rider dependency rules | QR-06 | Dependency rule bypass | Rider with a dependency (e.g. requires another rider or minimum face value) exists (CONFIRM). | 1. Select the dependent rider without its prerequisite. 2. Add the prerequisite and select again. | Dependent rider pair | Blocked or flagged without prerequisite; allowed with it. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 3 | @regression rider | Screenshots | Automated | tests/riders/riders.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-RID-09 | Removing a rider updates premium itemization and total | Riders | UI | Spec: premium itemization | QR-06, QR-05 | Premium not updated after rider removal | Application with one rider added. | 1. Note total premium with rider. 2. Remove the rider. 3. Read itemization and total. 4. Open review page. | ADB rider | Rider line removed; total returns to base premium; review page matches. | High | P2 | 3 | @regression rider | Screenshots | Automated | tests/riders/riders.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-01 | Add a valid primary beneficiary | Beneficiaries | UI | BEN-V01 | QR-07 | Beneficiary cannot be added | Application at Beneficiaries step. | 1. Fill valid individual beneficiary details with 100%. 2. Save. | Generated adult beneficiary | Beneficiary card/row appears; running total 100%. | High | P1 | 1 | @smoke @regression beneficiary | Screenshot | Automated | tests/beneficiaries/beneficiaries.spec.ts | Not run |  | Y | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-02 | Primary allocation below 100% blocks progression | Beneficiaries | UI | BEN-V02 | QR-07 | Allocation not 100% accepted | One primary beneficiary. | 1. Set primary total to 99%. 2. Proceed. | 99% | Error shown; progression blocked. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Critical | P1 | 2 | @regression beneficiary | Screenshot | Automated | tests/beneficiaries/allocation.spec.ts | Not run |  | Y | Boundary | API: POST /validate returns allocation error | Creates its own application via fixture (independent; unique generated data).
TC-BEN-03 | Primary allocation above 100% blocks progression | Beneficiaries | UI | BEN-V03 | QR-07 | Allocation not 100% accepted | Primary beneficiaries present. | 1. Set primary total to 101%. 2. Proceed. | 101% | Error shown; progression blocked. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Critical | P1 | 2 | @regression beneficiary | Screenshot | Automated | tests/beneficiaries/allocation.spec.ts | Not run |  | Y | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-04 | Secondary allocation is validated separately | Beneficiaries | UI | BEN-V04 | QR-07 | Secondary total not validated | Primary at 100%. | 1. Add secondary beneficiaries totalling 90%. 2. Proceed. 3. Correct to 100%. | Secondary 90% then 100% | 90% blocks with separate secondary-total error; 100% accepted; primary total unaffected. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 2 | @regression beneficiary | Screenshots | Automated | tests/beneficiaries/allocation.spec.ts | Not run |  | N | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-05 | Minor beneficiary requires guardian details | Beneficiaries | UI | BEN-V05 | QR-07 | Minor without guardian accepted | At Beneficiaries step. | 1. Add beneficiary with DOB 17y364d. 2. Leave guardian blank and save. 3. Fill guardian. | Minor DOB | Guardian fields appear and are mandatory; blank blocked; filled accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Critical | P1 | 2 | @regression beneficiary | Screenshots | Automated | tests/beneficiaries/minor.spec.ts | Not run |  | Y | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-06 | Trust beneficiary shows trust-specific fields | Beneficiaries | UI | BEN-V06 | QR-07 | Type-specific fields missing | Add beneficiary form open. | 1. Select type Trust. | Trust type | Trust Name, Trustee Name and Trust Date fields shown and mandatory. | Medium | P2 | 3 | @regression beneficiary | Screenshot | Automated | tests/beneficiaries/types.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-07 | Organization beneficiary shows organization fields | Beneficiaries | UI | BEN-V07 | QR-07 | Type-specific fields missing | Add beneficiary form open. | 1. Select type Organization. | Organization type | Registration and contact fields shown and mandatory. | Medium | P2 | 3 | @regression beneficiary | Screenshot | Automated | tests/beneficiaries/types.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-08 | Duplicate beneficiary (Name + DOB + Relationship) is blocked | Beneficiaries | UI | BEN-V08 | QR-07 | Duplicates allowed | One beneficiary already added. | 1. Add second beneficiary with same name, DOB and relationship. | Duplicate record | Duplicate error displayed; second record not added. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression beneficiary | Screenshot | Automated | tests/beneficiaries/duplicates.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-09 | Removing a beneficiary updates the allocation total | Beneficiaries | UI | BEN-V09 | QR-07 | Removal leaves wrong total | Two primary beneficiaries 60% / 40%. | 1. Remove the 40% beneficiary. 2. Read running total. | 60/40 split | Running total updates to 60% and the 100% error appears. | High | P2 | 2 | @regression beneficiary | Screenshot | Automated | tests/beneficiaries/allocation.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-10 | Irrevocable designation requires legal confirmation modal | Beneficiaries | UI | Spec: special designation | QR-07 | Irrevocable confirmation skipped | Add beneficiary form open. | 1. Mark beneficiary as irrevocable. 2. Save. 3. Cancel the modal, then retry and confirm. | Irrevocable flag | Confirmation modal appears; cancel keeps it unsaved as irrevocable; confirm saves. | Medium | P2 | 3 | @regression beneficiary | Screenshot of modal | Automated | tests/beneficiaries/special.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-11 | At least one primary beneficiary is mandatory | Beneficiaries | UI | Spec: primary beneficiary | QR-07, QR-09 | Missing primary beneficiary accepted | Application with no beneficiaries. | 1. Proceed from Beneficiaries step with none added. 2. Check review summary. | No beneficiaries | Progression/submission blocked and summary lists missing primary beneficiary. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 3 | @regression beneficiary | Screenshot | Automated | tests/beneficiaries/allocation.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-12 | Editing a beneficiary updates the record and allocation total | Beneficiaries | UI | Spec: add/edit/remove beneficiaries | QR-07, QR-10 | Edit not saved / total stale | One primary beneficiary at 100%. | 1. Edit the beneficiary's name and allocation to 50%. 2. Save. 3. Read card and running total. 4. Reload page. | Name change; 50% | Card shows new name; running total 50% with allocation error; values persist after reload. | Medium | P2 | 3 | @regression beneficiary | Screenshots | Automated | tests/beneficiaries/beneficiaries.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-13 | Invalid allocation inputs (0, negative, non-numeric, decimals) are handled | Beneficiaries | UI | Spec: allocation percentage validation | QR-07 | Invalid allocation accepted | Add beneficiary form open. | 1. Enter 0, -10, 'abc', 33.333, 100.01 as allocation. 2. Save. | 0; -10; 'abc'; 33.333; 100.01 | Each invalid value rejected (decimal behavior per confirmed rule); no beneficiary saved with invalid value. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P2 | 3 | @regression beneficiary | Screenshot per value | Automated | tests/beneficiaries/allocation.spec.ts | Not run |  | N | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-BEN-14 | Beneficiaries persist after save, navigation and resume | Beneficiaries | UI | Spec: persistence | QR-07, QR-10 | Beneficiary data not persisted | Application with 2 primary and 1 secondary beneficiary saved. | 1. Save and go to dashboard. 2. Resume the application. 3. Open Beneficiaries step. 4. (If available) compare with GET beneficiaries / DB rows. | 60/40 primary + 100 secondary | All beneficiaries, types, allocations and totals restored exactly; API/DB rows match. | High | P1 | 2 | @regression beneficiary | Screenshot + API/DB comparison | Automated | tests/beneficiaries/persistence.spec.ts | Not run |  | N | Positive | API: GET beneficiaries; DB beneficiary rows | Creates its own application via fixture (independent; unique generated data).
TC-DOC-01 | Valid KYC document uploads successfully | Documents & Validation | UI | DOC-V01 | QR-08 | Valid upload rejected | On Documents step. | 1. Upload small PDF, JPG and PNG. | fixtures/files/valid.* | Each file shows uploaded status. | High | P1 | 1 | @smoke @regression documents | Screenshot of statuses | Automated | tests/documents/upload.spec.ts | Not run |  | Y | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-DOC-02 | Unsupported file type is rejected on Documents step | Documents & Validation | UI | DOC-V02 | QR-08 | Bad file types accepted | On Documents step. | 1. Upload .exe and .txt files. | invalid files | Error message; no uploaded status. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression documents | Screenshot | Automated | tests/documents/upload.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-DOC-03 | File above maximum size is rejected | Documents & Validation | UI | DOC-V03 | QR-08 | Oversize files accepted | Max size known (CONFIRM). | 1. Upload file just above max size. 2. Upload file just below max. | Generated files max+1 byte / max-1 byte | Oversize rejected with size message; under-limit accepted. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | High | P1 | 2 | @regression documents | Screenshots | Automated | tests/documents/upload.spec.ts | Not run | Exact value/rule to be confirmed from app (see Open Items). | N | Boundary | API: POST documents rejects oversize | Creates its own application via fixture (independent; unique generated data).
TC-DOC-04 | Missing mandatory document blocks submission | Documents & Validation | UI | DOC-V04 | QR-08, QR-09 | Mandatory document not enforced | Otherwise complete application with no KYC document. | 1. Go to review. 2. Attempt to submit. | No documents | Summary lists missing document; submit blocked. Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Critical | P1 | 2 | @regression documents | Screenshot of summary | Automated | tests/documents/upload.spec.ts | Not run |  | Y | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-DOC-05 | Uploaded document status persists after reload and resume | Documents & Validation | UI | Spec: upload confirmation/status | QR-08, QR-10 | Upload status not stored | Valid document uploaded. | 1. Upload valid PDF. 2. Reload page. 3. Resume from dashboard. | valid.pdf | Document still listed as uploaded with correct name/status. | Medium | P2 | 3 | @regression documents | Screenshots | Automated | tests/documents/upload.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-VAL-01 | Validation summary lists all unresolved errors grouped | Documents & Validation | UI | VAL-V01 | QR-08 | Summary stale or incomplete | Incomplete application with several known gaps. | 1. Open /review for incomplete application. 2. Read summary. | Application missing client, doc, beneficiary data | Each known gap is listed, grouped by section; no phantom errors. | High | P1 | 2 | @regression documents | Screenshot of summary | Automated | tests/documents/validation-summary.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-VAL-02 | Clicking a validation error navigates to the field | Documents & Validation | UI | VAL-V02 | QR-08 | Error link does not focus field | Summary showing at least one error. | 1. Click an item in the summary. | Any error item | App navigates to the related section and focuses the field. | Medium | P2 | 3 | @regression documents | Screenshot / focus assertion | Automated | tests/documents/validation-summary.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-VAL-03 | Submit stays disabled until critical errors are resolved | Documents & Validation | UI | VAL-V03 | QR-08, QR-09 | Submit enabled with errors | Application with critical errors. | 1. Open /review for an application with critical errors; check Submit state. 2. Fix every error. 3. Re-check Submit state. | Application from TC-VAL-01 | Disabled while errors exist; enabled when clean; summary refreshes after upstream change (not stale). Also verify: the rejected value is not saved (reload or GET shows the previous/empty value). | Critical | P1 | 1 | @smoke @regression documents | Screenshots at each state | Automated | tests/documents/validation-summary.spec.ts | Not run |  | Y | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-VAL-04 | Validation summary refreshes after upstream data changes (not stale) | Documents & Validation | UI | Risk QR-08: summary stale | QR-08 | Validation summary stale | Application previously clean at review (submit enabled). | 1. Open /review: summary clean. 2. Go back and invalidate data (e.g. delete a beneficiary so total < 100%). 3. Return to /review. | Clean application | Summary now shows the new error and Submit is disabled; no stale 'clean' state. | High | P1 | 2 | @regression documents | Screenshots before and after | Automated | tests/documents/validation-summary.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-VAL-05 | Review page shows data consistent with what was entered | Documents & Validation | UI | Guideline: review consistency | QR-08, QR-10 | Review data differs from entered data | Fully completed application. | 1. Record values entered per step (client, address, product, riders, beneficiaries). 2. Open /review. 3. Compare each section. | Generated application | Every section on review equals entered values (names, DOB/age, product, face value, premium, riders, beneficiaries, documents). | High | P1 | 2 | @regression documents | Screenshot of review + comparison log | Automated | tests/documents/review.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-WF-01 | Incomplete application can be saved as draft | Submission & Status | UI | WF-V01 | QR-10 | Draft not persisted | Logged in; new application started. | 1. Enter partial client data. 2. Click Save draft. 3. Go to dashboard. | Partial client data | Dashboard shows a Draft row for the application. | High | P1 | 2 | @regression workflow | Screenshot of dashboard row | Automated | tests/workflow/draft.spec.ts | Not run |  | N | Positive | DB (if approved): status = Draft | Creates its own application via fixture (independent; unique generated data).
TC-WF-02 | Draft resumes with saved data at correct step | Submission & Status | UI | WF-V02 | QR-10 | Draft data lost | Draft from TC-WF-01. | 1. Open draft from dashboard. 2. Inspect values. | Draft created in setup | Saved values and step restored. | High | P1 | 2 | @regression workflow | Screenshot | Automated | tests/workflow/draft.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-WF-03 | Valid application is submitted end to end and gets a reference number | Submission & Status | E2E | WF-V03 | QR-09 | Incomplete/no reference on submit | Valid agent; all test files and data available. | 1. Login. 2. Start new application. 3. Complete Client, Address, KYC, Product, Riders, Beneficiaries, Documents. 4. Review summary clean. 5. Submit. 6. Read confirmation. | Generated valid application | Confirmation shows non-empty reference number; no validation errors. | Critical | P1 | 1 | @smoke @e2e workflow | Trace of full flow; confirmation screenshot | Automated | tests/workflow/e2e-submission.spec.ts | Not run |  | Y | Positive | API: status = Submitted; DB: reference unique | Creates its own application; submission cannot be undone - unique generated data.
TC-WF-04 | Submitted application is read-only | Submission & Status | UI | WF-V04 | QR-09 | Submitted app editable | Submitted application exists. | 1. Open submitted application. 2. Try editing fields and saving. | Submitted application id | Fields disabled/read-only; edit controls absent. | High | P1 | 2 | @regression workflow | Screenshot | Automated | tests/workflow/submission.spec.ts | Not run |  | N | Positive | API: POST update rejected for submitted application | Read-only seeded submitted application.
TC-WF-05 | Confirmation/status message shown after submission | Submission & Status | UI | WF-V05 | QR-09 | Missing confirmation | Run in E2E flow. | 1. Submit valid application. 2. Read confirmation page. | - | Confirmation message (email simulation/status) displayed. | Medium | P2 | 2 | @regression workflow | Screenshot | Automated | tests/workflow/submission.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-WF-06 | Dashboard status updates to Submitted after submission | Submission & Status | UI | WF-V06 | QR-02, QR-09 | Wrong status on dashboard | Application just submitted. | 1. Go to dashboard. 2. Find the application. | Submitted application | Status shows Submitted. | High | P1 | 2 | @regression workflow | Screenshot | Automated | tests/workflow/submission.spec.ts | Not run |  | N | Positive | API: GET status | Creates its own application via fixture (independent; unique generated data).
TC-WF-07 | Application detail status matches status API | Submission & Status | UI | WF-V07 | QR-09 | Status differs from backend | Submitted application. | 1. Open /applications/:id/status. 2. Call GET /api/applications/{id}/status. 3. Compare. | Submitted application | UI status equals API status. | High | P2 | 2 | @regression workflow @api | UI vs API values in log | Automated | tests/workflow/status.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-WF-08 | Reference numbers are unique across submissions | Submission & Status | E2E | Risk QR-09 | QR-09 | No or duplicate reference number | Two valid applications ready to submit. | 1. Submit application A; note reference. 2. Submit application B; note reference. | Two generated applications | References are non-empty and different. | High | P2 | 3 | @regression @e2e workflow | Both references in log | Automated | tests/workflow/e2e-submission.spec.ts | Not run |  | N | Positive | - | Creates two applications; unique data.
TC-WF-09 | Status history records Draft to Submitted with timestamps | Submission & Status | UI | Risk QR-09 | QR-09, QR-10 | Status history gaps | Submitted application. | 1. Open /applications/:id/status. 2. Read history entries. | Submitted application | History contains Draft and Submitted entries in order with timestamps. | Medium | P3 | 3 | @regression workflow | Screenshot of history | Automated | tests/workflow/status.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-WF-10 | Smoke path: login, create application, complete main screens, reach review | Submission & Status | E2E | Guideline build sequence step 5 | QR-09, QR-10 | Main flow broken before review | Valid agent; test files available. | 1. Login. 2. Start new application. 3. Complete Client, Address, KYC, Product, Riders, Beneficiaries, Documents. 4. Open /review. | Generated valid application | Every step advances; review page opens with an empty summary and Submit enabled (no submission performed). | Critical | P1 | 1 | @smoke @e2e workflow | Trace of complete path; screenshot of review | Automated | tests/workflow/smoke-to-review.spec.ts | Not run |  | Y | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-WF-11 | Re-submitting a submitted application does not create a second reference or change status | Submission & Status | E2E | Risk QR-09: duplicate reference | QR-09 | Duplicate reference / double submit | Submitted application; double-click possible on submit button. | 1. Submit a valid application with a rapid double click. 2. Note reference. 3. POST /api/applications/{id}/submit again. 4. Read status and reference. | Valid application | Only one reference exists; second submit is rejected or idempotent; status remains Submitted; history shows one Submitted entry. | High | P2 | 3 | @regression @e2e workflow | API response + status history | Automated | tests/workflow/submission.spec.ts | Not run |  | N | Negative | - | Creates its own application; unique data.
TC-WF-12 | Confirmation page is not reachable for an unsubmitted application | Submission & Status | UI | Route /confirmation state check | QR-09 | Confirmation shown without submission | Draft application. | 1. Open /applications/<draftId>/confirmation directly. | Draft id | No reference/success message shown; user is redirected to the current step or review. | Medium | P2 | 3 | @regression workflow | Screenshot | Automated | tests/workflow/submission.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-WF-13 | Submitted data matches entered data (persistence UI/API/DB) | Submission & Status | E2E | Risk QR-10 | QR-10, QR-09 | Data not persisted accurately | Application submitted in E2E; API access (DB read-only if approved). | 1. Record entered data. 2. Submit. 3. Open submitted application read-only view. 4. GET application detail via API (and DB query if allowed). | Generated application | Read-only view and API/DB values equal the entered values; sensitive fields remain masked. | High | P2 | 3 | @regression @e2e workflow | Comparison log; query output (redacted) | Automated | tests/workflow/persistence.spec.ts | Not run |  | N | Positive | API/DB: stored values equal entered values | Creates its own application via fixture (independent; unique generated data).
TC-API-01 | GET /api/products returns 200 and expected schema | API | API | API-V01 | QR-05 | Product schema broken | Authenticated request context. | 1. GET /api/products. 2. Assert status and keys/types for each product. | Session/token | 200; each product has required keys (id, name, status, limits...) with correct types. | Medium | P1 | 1 | @api @smoke products | Response body | Automated | tests/api/products-api.spec.ts | Not run |  | Y | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-API-02 | Protected APIs require authorization (no token, invalid token) | API | API | API-V02 | QR-01 | API reachable without auth | No token/session. | 1. Call GET /api/applications, /api/applications/{id}/client, /status and POST /submit with no credentials. 2. Repeat with an invalid/expired token. | None / invalid token | 401 or 403; no application data in body. | Critical | P1 | 1 | @api @smoke auth | Status + body | Automated | tests/api/auth-api.spec.ts | Not run |  | Y | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-API-03 | Client API rejects invalid DOB | API | API | API-V03 | QR-03 | UI and API rules differ | Authenticated; application id owned. | 1. POST client payload with future DOB. 2. POST with underage DOB. 3. GET client to confirm nothing saved. | Future and underage DOBs | 4xx validation error with error structure; invalid DOB not persisted. | Critical | P1 | 2 | @api @regression client | Request/response | Automated | tests/api/client-api.spec.ts | Not run |  | Y | Boundary | - | Creates its own application via fixture (independent; unique generated data).
TC-API-04 | Validation API returns beneficiary allocation error | API | API | API-V04 | QR-07 | UI and API rules differ | Application with 90% primary allocation. | 1. POST /api/applications/{id}/validate. | Under-allocated beneficiaries | Response lists allocation error in expected error structure. | High | P1 | 2 | @api @regression beneficiary | Response body | Automated | tests/api/validation-api.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-API-05 | Submission API rejects incomplete application | API | API | API-V05 | QR-09 | Incomplete application submits | Draft application with missing sections. | 1. POST /api/applications/{id}/submit. 2. GET status. | Incomplete draft | Error response; no reference number; status remains Draft. | Critical | P1 | 2 | @api @regression workflow | Response + status | Automated | tests/api/submission-api.spec.ts | Not run |  | Y | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-API-06 | Applications list API matches dashboard rows (list endpoint) | API | API | API-V06 | QR-02 | Dashboard status differs from backend | Valid agent with applications. | 1. GET /api/applications. 2. Read dashboard rows (id, status, name). 3. Compare ids, count and statuses. | Seeded applications | Same applications and statuses in API and UI. | High | P2 | 2 | @api @regression dashboard | Comparison table | Automated | tests/api/applications-api.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-API-07 | Product detail API matches UI detail page | API | API | API-V07 | QR-05 | Product data mismatch | Authenticated. | 1. GET /api/products/{id}. 2. Open same product in UI. 3. Compare limits/terms/features. | First active product | Fields match between API and UI. | Medium | P2 | 3 | @api @regression product | Comparison in log | Automated | tests/api/products-api.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-API-08 | Applications API returns only logged-in agent's records | API | API | API-V08 | QR-02 | Cross-agent data exposure | Two agents with applications. | 1. GET /api/applications as agent A and B. 2. Request agent A's application id as agent B. | VALID_AGENT, SECOND_AGENT | Lists do not overlap; cross-agent id returns 403/404. | Critical | P1 | 2 | @api @regression dashboard | Both responses | Automated | tests/api/applications-api.spec.ts | Not run |  | Y | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-API-09 | Login API rejects invalid credentials | API | API | Spec: POST /api/auth/login | QR-01 | Misleading login response | None. | 1. POST /api/auth/login with wrong password. 2. POST with unknown user. 3. POST with valid credentials. | Wrong/unknown/valid | 401 for invalid cases with consistent error structure; 200 with token/session for valid. | High | P1 | 2 | @api @regression auth | Responses (token redacted) | Automated | tests/api/auth-api.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-API-10 | Riders API returns schema, categories and eligibility data | API | API | Spec: GET /api/riders | QR-06 | Rider data/contract broken | Authenticated. | 1. GET /api/riders. 2. Validate keys/types; check eligibility and dependency fields exist. | Session | 200; each rider has id, name, category, eligibility/limit fields with correct types; matches UI rider list. | Medium | P2 | 2 | @api @regression rider | Response body | Automated | tests/api/riders-api.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-API-11 | Beneficiaries API enforces allocation, minor guardian and duplicate rules | API | API | Spec: POST /api/applications/{id}/beneficiaries | QR-07 | UI and API rules differ | Authenticated; application id owned. | 1. POST beneficiaries totalling 99% / 101%. 2. POST minor without guardian. 3. POST duplicate (name+DOB+relationship). 4. GET beneficiaries to confirm none persisted. | Invalid payloads | Each rejected with 4xx and structured errors; GET shows rejected data not stored. | High | P1 | 2 | @api @regression beneficiary | Request/response pairs | Automated | tests/api/beneficiaries-api.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-API-12 | Documents API rejects unsupported type and oversize files | API | API | Spec: POST /api/applications/{id}/documents | QR-08 | UI and API rules differ | Authenticated; application id owned. | 1. POST .exe file. 2. POST file above max size. 3. POST valid PDF. | fixtures/files | Invalid type and oversize rejected (4xx, structured error); valid file accepted and status retrievable. | High | P2 | 3 | @api @regression documents | Responses | Automated | tests/api/documents-api.spec.ts | Not run |  | N | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-API-13 | Client API persistence and required-field validation errors | API | API | Spec: GET/POST /api/applications/{id}/client | QR-03, QR-10 | Client data not persisted / errors unstructured | Authenticated; new application id. | 1. POST client with required fields missing. 2. POST valid client. 3. GET client. | Incomplete / valid payloads | Missing fields produce 4xx with field-level errors; valid POST then GET returns the same values. | High | P2 | 2 | @api @regression client | Responses | Automated | tests/api/client-api.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-API-14 | Status API returns current status, history and timestamps | API | API | Spec: GET /api/applications/{id}/status | QR-09 | Status history gaps | Submitted and draft applications. | 1. GET status for a draft. 2. GET status for a submitted application. | Seeded draft + submitted | Draft: status Draft; submitted: status Submitted with history entries in order and valid timestamps. | Medium | P2 | 3 | @api @regression workflow | Responses | Automated | tests/api/status-api.spec.ts | Not run |  | N | Positive | - | Creates its own application via fixture (independent; unique generated data).
TC-API-15 | UI and API give the same verdict for the same invalid input (rule parity) | API | API | Problem statement 2.2: API validation differs from UI | QR-03, QR-07, QR-09 | UI and API rules differ | Authenticated; UI and API tests run on the same data set. | 1. For each case (future DOB, underage DOB, allocation 99%, minor w/o guardian) submit via UI and via API. 2. Compare accept/reject outcome. | Shared invalid datasets | Outcome is identical in UI and API for every case; any difference is logged as a defect. | Critical | P1 | 3 | @api @regression | Parity table in test log | Automated | tests/api/parity.spec.ts | Not run |  | Y | Negative | - | Creates its own application via fixture (independent; unique generated data).
TC-XC-01 | Smoke login and dashboard on Firefox and WebKit | Cross-Cutting | UI | Risk QR-13 cross-browser | QR-13 | Critical flow differs on another browser | Playwright projects for firefox and webkit configured. | 1. Run @smoke auth and dashboard tests with --project=firefox and --project=webkit. | VALID_AGENT | Login and dashboard smoke pass on both browsers or differences are logged as browser defects. | Medium | P3 | 3 | @smoke cross-browser | HTML report per project | Automated | tests/auth/login.spec.ts (projects) | Not run |  | N | Positive | - | Read-only (login only).

## Coverage Summary
Coverage by Module vs Minimum Automation Coverage
Minimums are from 'Submissions and Evaluations' section 5.5 (blue = hard-coded input from the source document). Counts are live formulas on the Test Cases sheet.
Module | Minimum Required (60-test target) | Planned Test Cases | Wave 1 (Smoke) | P1 Cases | Critical Severity | Surplus / (Gap) vs Minimum | Status
Authentication | 6
Dashboard | 4
Client Information | 8
Address & Contact | 5
KYC & Financial | 6
Product & Policy | 6
Riders | 5
Beneficiaries | 7
Documents & Validation | 4
Submission & Status | 5
API | 8
Cross-Cutting | 0
TOTAL
Reduced-scope option
Short-cohort set (30-35 tests): Wave 1 + all Critical cases + 5 extras (lockout, rider rules, premium) so auth, one E2E, allocation, rider rules, API and reporting stay covered. Count flagged 'Y':
Wave 1 (smoke) cases:
Automation progress
Not started
In progress
Automated
Manual only
Blocked
Not applicable
Test type split
UI
API
E2E
Scenario mix (guards against happy-path-only suites)
Positive
Negative
Boundary
Negative + Boundary share (target: at least 50%)

## Risk Traceability
Traceability: Submission 1 Risk Register (QR-01..QR-14) to Test Cases
Risk ID | Area | Risk (from Submission 1) | Priority | # Test Cases | Coverage
QR-01 | Authentication | Unauthorized protected-route or API access | Critical
QR-02 | Dashboard | Cross-agent data exposure or incorrect status | Critical
QR-03 | Client | DOB boundary or age calculation failure | Critical
QR-04 | KYC/Compliance | Sensitive ID exposure or mandatory evidence bypass | Critical
QR-05 | Product/Premium | Invalid configuration or inconsistent premium | Critical
QR-06 | Riders | Eligibility, coverage, count or exclusion rule bypass | Critical
QR-07 | Beneficiaries | Invalid allocation, duplicate or missing guardian accepted | Critical
QR-08 | Documents/Review | Invalid upload or stale validation summary | High
QR-09 | Submission | Incomplete case submits or reference/state is wrong | Critical
QR-10 | Persistence | Draft or submitted values not saved accurately | High
QR-11 | Automation | Flaky checks or weak evidence hides true result | Medium
QR-12 | Test Data | Seed collision or reset changes expected state | High
QR-13 | Cross-browser | Critical workflow differs on supported browser | Medium
QR-14 | Environment | Shared service or dependency prevents valid testing | High
QR-11 to QR-14 are addressed by framework design, not individual test cases: stable locators and trace/screenshot config (QR-11), unique generated data per run plus reserved seed users (QR-12), the Chromium/Firefox/WebKit projects in playwright.config.ts (QR-13), and a health-check / global-setup step (QR-14). They are documented in the README.

## Validation ID Matrix
Every Validation ID in the problem statement mapped to a test case
Validation ID | Scenario (from Functional Module Descriptions) | Mapped Test Case(s) | # Mapped | Status
AUTH-V01 | Valid agent can log in successfully | TC-AUTH-01
AUTH-V02 | Invalid password displays correct error message | TC-AUTH-02
AUTH-V03 | Blank username and password show mandatory validation | TC-AUTH-03
AUTH-V04 | Logout clears session and redirects to login page | TC-AUTH-04
AUTH-V05 | Direct access to dashboard without login is blocked | TC-AUTH-05
AUTH-V06 | Locked user cannot access dashboard | TC-AUTH-06
AUTH-V07 | Account locks after five failed login attempts | TC-AUTH-07
AUTH-V08 | Password policy rejects weak password | TC-AUTH-08
DASH-V01 | Dashboard loads after successful login | TC-DASH-01
DASH-V02 | Agent sees only own applications | TC-DASH-02
DASH-V03 | New agent sees empty application state | TC-DASH-03
DASH-V04 | Draft application can be resumed | TC-DASH-04
DASH-V05 | Application status filter works correctly | TC-DASH-05
DASH-V06 | Dashboard application status matches API response | TC-DASH-06
CLI-V01 | Agent can enter valid insured personal information | TC-CLI-01
CLI-V02 | Mandatory personal fields are validated | TC-CLI-02
CLI-V03 | DOB below 18 years is rejected | TC-CLI-03
CLI-V04 | DOB above 65 years is rejected | TC-CLI-04
CLI-V05 | Future DOB is rejected | TC-CLI-05
CLI-V06 | Same-as-residential address copies data to mailing address | TC-ADDR-01
CLI-V07 | Invalid email and phone formats are rejected | TC-ADDR-05, TC-ADDR-06
CLI-V08 | SSN is masked after entry | TC-KYC-01
CLI-V09 | KYC upload rejects unsupported file type | TC-KYC-03
CLI-V10 | PEP Yes requires additional details | TC-KYC-04
PROD-V01 | Product catalog displays expected Whole Life products | TC-PROD-01
PROD-V02 | Product details page opens correctly | TC-PROD-02
PROD-V03 | Face value below minimum is rejected | TC-PROD-03
PROD-V04 | Face value above maximum is rejected | TC-PROD-04
PROD-V05 | Premium recalculates when frequency changes | TC-PROD-05
PROD-V06 | Premium on review page matches configuration page | TC-PROD-06
PROD-V07 | Product suitability warning appears for mismatch | TC-PROD-07
RIDER-V01 | Agent can add an eligible protection rider | TC-RID-01
RIDER-V02 | Rider coverage cannot exceed base face value | TC-RID-02
RIDER-V03 | Age-ineligible rider cannot be added | TC-RID-03
RIDER-V04 | Maximum rider count is enforced | TC-RID-04
RIDER-V05 | Mutually exclusive waiver riders cannot both be selected | TC-RID-05
RIDER-V06 | Critical illness rider triggers health questionnaire | TC-RID-06
RIDER-V07 | Rider premium is itemized in total premium | TC-RID-07
BEN-V01 | Add a valid primary beneficiary | TC-BEN-01
BEN-V02 | Primary allocation below 100% blocks progression | TC-BEN-02
BEN-V03 | Primary allocation above 100% blocks progression | TC-BEN-03
BEN-V04 | Secondary allocation is validated separately | TC-BEN-04
BEN-V05 | Minor beneficiary requires guardian details | TC-BEN-05
BEN-V06 | Trust beneficiary shows trust-specific fields | TC-BEN-06
BEN-V07 | Organization beneficiary shows organization-specific fields | TC-BEN-07
BEN-V08 | Duplicate beneficiary is blocked | TC-BEN-08
BEN-V09 | Removing beneficiary updates allocation total | TC-BEN-09
DOC-V01 | Valid KYC document can be uploaded | TC-DOC-01
DOC-V02 | Unsupported file type is rejected | TC-DOC-02
DOC-V03 | File above maximum size is rejected | TC-DOC-03
DOC-V04 | Missing mandatory document blocks submission | TC-DOC-04
VAL-V01 | Validation summary lists all unresolved errors | TC-VAL-01
VAL-V02 | Clicking validation error navigates to field | TC-VAL-02
VAL-V03 | Submit button remains disabled until critical errors are resolved | TC-VAL-03
WF-V01 | Agent can save incomplete application as draft | TC-WF-01
WF-V02 | Draft application can be resumed with saved data | TC-WF-02
WF-V03 | Valid application can be submitted successfully | TC-WF-03
WF-V04 | Submitted application becomes read-only | TC-WF-04
WF-V05 | Confirmation email simulation/status message appears after submission | TC-WF-05
WF-V06 | Dashboard status updates after submission | TC-WF-06
WF-V07 | Application detail status matches API response | TC-WF-07
API-V01 | Products API returns 200 and expected schema | TC-API-01
API-V02 | Application API requires authorization | TC-API-02
API-V03 | Client API rejects invalid DOB | TC-API-03
API-V04 | Validation API returns beneficiary allocation error | TC-API-04
API-V05 | Submission API rejects incomplete application | TC-API-05
API-V06 | Application status API matches dashboard | TC-API-06
API-V07 | Product API supports product detail retrieval | TC-API-07
API-V08 | Applications API returns only logged-in agent records | TC-API-08
Validation IDs without a test case:

## Test Data
Controlled Test Data (generated per run; never hard-code in specs)
Boundary DOBs are formulas relative to today so the sheet always shows the dates for the day you read it. dataGenerator.ts must compute the same values at run time.
Dataset | Date of Birth (calculated) | Expected Outcome | Used By
Underage - 17 years 364 days |  | Rejected (below 18) | TC-CLI-03, TC-API-03, TC-BEN-05 (as minor)
Exactly 18 years |  | Accepted (confirm inclusive) | TC-CLI-06
Typical adult - 40 years |  | Accepted | TC-CLI-01, TC-WF-03
Exactly 65 years |  | Accepted (confirm inclusive) | TC-CLI-06
Over 65 - 65 years + 1 day |  | Rejected (above 65) | TC-CLI-04
Future date - tomorrow |  | Rejected | TC-CLI-05, TC-API-03
Allocation datasets
Scenario | Primary % | Secondary % | Expected
Exact | 100 | 100 | Accepted
Under | 99 | - | Blocked
Over | 101 | - | Blocked
Split 60/40 | 60 + 40 | - | Accepted; removing 40 leaves 60 -> error
Secondary short | 100 | 90 | Blocked (secondary total)
Upload files (fixtures/files)
File | Type / Size | Expected | Used By
valid.pdf | PDF, ~50 KB | Accepted | TC-DOC-01
valid.jpg | JPG, ~50 KB | Accepted | TC-DOC-01
valid.png | PNG, ~50 KB | Accepted | TC-DOC-01
invalid.exe | EXE (renamed dummy) | Rejected - type | TC-KYC-03, TC-DOC-02
invalid.txt | TXT | Rejected - type | TC-KYC-03, TC-DOC-02
under-limit.pdf | max size - 1 byte (CONFIRM max) | Accepted | TC-DOC-03
over-limit.pdf | max size + 1 byte (CONFIRM max) | Rejected - size | TC-DOC-03
Environment variables (.env.example placeholders - no real values)
Variable | Purpose | Placeholder
BASE_URL | App base URL | http://127.0.0.1:8081
APP_NAME | insurance or finserve | insurance
VALID_AGENT_USER / _PASS | Happy path agent | <from seed data doc>
SECOND_AGENT_USER / _PASS | Data isolation | <from seed data doc>
NEW_AGENT_USER / _PASS | Empty dashboard | <from seed data doc>
LOCKED_AGENT_USER / _PASS | Locked message | <from seed data doc>
LOCKOUT_TEST_AGENT_USER / _PASS | Reserved for 5-attempt lock test | <from seed data doc>
MFA_AGENT_USER / _PASS / MFA_OTP | OTP login | <from seed data doc>
API_BASE_URL | API root | ${BASE_URL}/api
SEEDED_DRAFT_ID / SEEDED_SUBMITTED_ID | Resume and read-only checks | <from seed data doc>

## Open Items
Values to confirm from the running app / mentor before asserting exact results
# | Item to confirm | Why it matters | Affected Test Cases | Resolution (fill in) | Status
1 | Insurance app port (8081 vs 8082) and base URL | FinServe app also runs in the lab | All |  | Open
2 | Seed users, passwords, MFA OTP value, lockout reset method | Auth and isolation tests | TC-AUTH-*, TC-DASH-02/03, TC-API-08 |  | Open
3 | Are ages 18 and 65 inclusive? Timezone for age calculation? | Boundary assertions | TC-CLI-03/04/06 |  | Open
4 | Password policy and failed-attempt/lock-reset rules | Exact weak-password set | TC-AUTH-07/08/11 |  | Open
5 | Product face value min/max, payment and policy terms, active vs inactive products | Boundary values | TC-PROD-* |  | Open
6 | Premium formula/rounding or API field exposing premium | Recalculation assertions | TC-PROD-05/06, TC-RID-07 |  | Open
7 | Rider age limits, max rider count, coverage caps, waiver pair | Rider decision table | TC-RID-* |  | Open
8 | ID types and number formats; SSN mask format | KYC validation | TC-KYC-01/02/07 |  | Open
9 | Affordability rule (income vs premium) | Warning vs block | TC-KYC-05 |  | Open
10 | Allowed file types, max file size, mandatory documents by scenario | Upload tests | TC-KYC-03, TC-DOC-* |  | Open
11 | Duplicate beneficiary exact key and irrevocable modal wording | Duplicate/special tests | TC-BEN-08/10 |  | Open
12 | Seeded defect catalog / defect codes | Replace descriptive defect links with codes | All (column G) |  | Open
13 | Real data-testid / label names and API error structure | Locators and API assertions | All |  | Open
14 | Database access, schema and read-only credentials | Persistence evidence | TC-DASH-04, TC-WF-01/02, TC-WF-13 |  | Open
15 | Session timeout duration and behavior with unsaved edits | Expiry test design | TC-AUTH-12 |  | Open
16 | Pending-agent behavior and message | Expected result wording | TC-AUTH-13 |  | Open
17 | Product age-eligibility ranges and term combinations | Eligibility and term assertions | TC-PROD-10/11 |  | Open
18 | Rider dependency pairs and exclusive waiver pair | Decision-table data | TC-RID-05/08 |  | Open
19 | ID issue/expiry validation rules; allocation decimal rule | Boundary assertions | TC-KYC-09, TC-BEN-13, TC-PROD-12 |  | Open
20 | Dashboard and catalog search fields (name, reference, product) | Search assertions | TC-DASH-07, TC-PROD-13 |  | Open

## Review Log
Reviewer Findings and Changes Applied (v2 review against Submission 2 documents)
# | Type | Finding | Source requirement | Action taken | Test case(s)
1 | Gap | No test for session timeout / expiry | Auth automation focus: session timeout; Sub 1 path 'Session expiration' | Added session-expiry test | TC-AUTH-12
2 | Gap | Pending (unapproved) agent role not tested | Auth user types; Sub 1 roles table | Added pending-agent access test | TC-AUTH-13
3 | Gap | Dashboard search and profile/support routes not covered | Dashboard: search, filters; routes /profile, /support | Added search and route tests | TC-DASH-07, TC-DASH-09
4 | Gap | Cross-agent access only tested via lists, not direct URL | Risk QR-02 (Critical) | Added direct-URL isolation test | TC-DASH-08
5 | Gap | Impossible/malformed DOB values not tested | Client DOB boundaries, date validation | Added malformed DOB test | TC-CLI-09
6 | Gap | Financial suitability fields (income, net worth, source of funds, risk profile) and ID expiry not validated | KYC and financial spec | Added two KYC tests | TC-KYC-08, TC-KYC-09
7 | Gap | Product eligibility vs client age was missing although listed in problem statement 2.2 | Problem statement 2.2 | Added eligibility test (High, P1) | TC-PROD-10
8 | Gap | Payment/policy term rules, invalid face-value inputs, catalog search and UI-vs-API premium not covered | Product spec table; ProductCatalogPage; premium API reconciliation | Added four product tests | TC-PROD-11..14
9 | Gap | Rider dependency rules and rider removal not covered | Rider spec: dependency rules; premium itemization | Added two rider tests | TC-RID-08, TC-RID-09
10 | Gap | Beneficiary edit, invalid allocation inputs and persistence not covered | Beneficiary spec: add/edit/remove; allocation; persistence | Added three beneficiary tests | TC-BEN-12..14
11 | Gap | Validation summary staleness was bundled inside the submit-gating test; review data consistency and upload persistence missing | Guideline: review consistency; Risk QR-08 | Split stale-summary into its own test; added review-consistency and upload-persistence tests | TC-VAL-03/04/05, TC-DOC-05
12 | Gap | No smoke path that stops at review (guideline build step 5); no double-submit, confirmation gating or submitted-data persistence tests | Guideline 4 step 5; Risk QR-09, QR-10 | Added four workflow tests | TC-WF-10..13
13 | Gap | API areas with no test: riders, beneficiaries, documents, client GET/persistence, status history | Functional spec 3.9 API validation scope | Added five API tests | TC-API-10..14
14 | Gap | No test proving UI and API apply the same rules (explicit business problem) | Problem statement 2.2: API validation differs from UI | Added data-driven parity test (Critical) | TC-API-15
15 | Gap | Cross-browser risk QR-13 had no test | Sub 1 browser plan | Added Firefox/WebKit smoke case | TC-XC-01
16 | Weak | Ambiguous expected results ('Error shown; progression blocked') for allocation tests | Guideline: observable expected results | Rewrote with running-total value, blocked action and review-summary check | TC-BEN-02, TC-BEN-03
17 | Weak | Login negative test did not check user enumeration | AUTH-V02 and misleading-message risk | Added unknown-user step; same-message assertion | TC-AUTH-02
18 | Weak | Lockout test did not assert attempts 1-4 stay unlocked or persistence | AUTH-V07 | Expanded expected result | TC-AUTH-07
19 | Weak | API-02 only checked one endpoint | API-V02 'requires authorization' | Now loops over multiple protected endpoints with no and invalid token | TC-API-02
20 | Overlap | DASH-06 and API-06 both compared status with API | Avoid duplicate coverage | Differentiated: status endpoint (DASH-06) vs list endpoint (API-06) | TC-DASH-06, TC-API-06
21 | Quality | Negative tests did not prove invalid data is not stored | Spec 7.9 persistence: rejected inputs not persisted | Added 'not saved' check to every negative/boundary UI test in data modules | All negative UI cases
22 | Quality | No indication of positive vs negative balance | Common mistake: happy-path only | Added Scenario Type column and mix table on Coverage Summary | All
23 | Quality | Backend verification not visible per test | Sub 1 layered validation (UI/API/DB) | Added Backend Cross-check column for key tests | 20 cases
24 | Quality | Test independence and shared-state risk not recorded | Best practice: independent tests; QR-12 seed collision | Added Isolation / Cleanup column; lockout and reset tests flagged serial/reserved | All
25 | Quality | Short-cohort fallback was a loose rule | Min coverage 30-35 option | Defined an explicit flagged set that keeps auth, E2E, allocation, rider rules, API | Short-Cohort Set = Y